BLAST RADIUS

# Blast Radius — 3-Week MVP Implementation Plan

Team Structure, Repository Setup, Dependencies, GitHub Prerequisites, Execution Plan & Delivery Checklist

Working execution plan for a six-person team | September 2026

Purpose Build and demonstrate a reusable, configuration-driven Blast Radius capability in three weeks. The analyzer is developed once in its own repository and exercised against three separate C#/.NET demo repositories.

# Contents

1. Executive Overview

2. Repository Strategy

3. Producer/API Demo Repository

4. Consumer 1 Demo Repository

5. Consumer 2 Demo Repository

6. Repository Workstream Mapping

7. Six Workstreams

8. Required Prerequisites

9. GitHub Prerequisites & Approvals

10. Secrets & Security

11. GitHub Branching Strategy

12. Configuration Design

13. Shared Data Contracts

14. Week 1 — Foundation

15. Week 2 — Core Implementation

16. Week 3 — Integration & Stabilization

17. Demo Scenario

18. Integration Architecture

19. Dependency Matrix

20. Cross-Team Dependency Rules

21. Definition of Done

22. What We Should NOT Build

23. Final Checklist Before Coding Starts

24. START HERE — First 4 Hours

Reading order Use Sections 1–7 for scope, repositories and ownership. Use Sections 8–13 to complete setup and agree contracts. Sections 14–20 are the schedule and integration rules. Sections 21–24 are the acceptance gate and Day 1 operating checklist.

# 1. Executive Overview

The team will build Blast Radius as a reusable analyzer in a dedicated Python repository, then validate it against three intentionally small C#/.NET application repositories. The three-week plan prioritizes a complete vertical slice in Week 1, real contract and impact intelligence in Week 2, and reliability plus demo readiness in Week 3.

Developer creates GitHub PR ↓ GitHub Actions triggers ↓ Python Blast Radius Orchestrator ↓ Git Diff / Contract Analysis ↓ Dependency & Impact Analysis ↓ AI Reasoning ↓ Relevant Test Selection ↓ Existing Repository Test Execution ↓ Failure Analysis ↓ Risk/Impact Report ↓ GitHub PR Comment + Streamlit Dashboard

Guiding principle Use code for facts, AI for reasoning, and configuration for reuse.

Build separately: the Blast Radius analyzer is independent from the sample application repositories.

Keep facts deterministic: Git diff, contract comparison, graph traversal, test selection and test execution remain code-owned.

Use AI for judgment: consumer impact, failure explanation, recommendations and narrative are schema-validated AI outputs.

Prove reuse: the same analyzer is configured against the three demo repositories without changing core Python code.

# 2. Repository Strategy

The MVP uses exactly four repositories. One repository contains the reusable Blast Radius product. Three repositories contain the deliberately small producer and consumer applications used to prove cross-repository impact analysis.

## Repository 1 — Blast Radius Analyzer

Suggested name: blast-radius

Purpose: the actual reusable Blast Radius product. Approved MVP technologies are Python 3.12, Streamlit, NetworkX, Pydantic, YAML, Git diff, OpenAPI/oasdiff where applicable, an enterprise-approved provider-agnostic LLM, GitHub API/CLI or a lightweight Python GitHub library, and GitHub Actions.

blast-radius/ ├── action.yml ├── README.md ├── requirements.txt ├── pyproject.toml ├── src/ │ ├── orchestrator/ │ ├── analyzers/ │ ├── graph/ │ ├── ai/ │ ├── tests/ │ ├── report/ │ └── ci/ ├── config/ │ ├── services.yaml │ └── rules.yaml ├── prompts/ │ ├── contract_analysis.md │ ├── consumer_impact.md │ ├── test_analysis.md │ ├── failure_analysis.md │ └── report_generation.md ├── graph/ │ └── graph.json └── .github/ └── workflows/

| Directory/file | Responsibility |
| --- | --- |
| action.yml | Reusable GitHub Action entry point; passes PR context and secrets to Python. |
| src/orchestrator | Coordinates configuration, analyzers, graph traversal, AI modules, tests and reporting. |
| src/analyzers | Deterministic Git diff, lightweight C# contract parsing and OpenAPI/oasdiff adapters. |
| src/graph | Builds and traverses NetworkX data and persists graph.json. |
| src/ai | Provider-agnostic LLM adapter, prompts, Pydantic output validation and guardrails. |
| src/tests | Unit and integration tests for analyzer behavior and orchestration boundaries. |
| src/report | Risk calculation, Markdown PR comment and report model rendering. |
| src/ci | GitHub integration; other CI hosts remain future adapters. |
| config/ | Project-specific registry and risk rules; core Python remains reusable. |
| prompts/ | Versioned prompt inputs for the five AI modules. |
| graph/ | Generated JSON graph of services, contracts, consumers, handlers and tests. |

# 3. Producer/API Demo Repository

## Repository 2 — blast-radius-demo-api

Purpose: a small C# producer/API repository used to demonstrate a contract or API change. It uses the existing .NET SDK appropriate for the demo repository, OpenAPI where applicable, and its existing repository test framework.

Minimal producer/API implementation

Contract/model

OpenAPI specification if applicable

A small set of tests

One intentionally designed breaking and one additive change scenario

OrderCreated ├── OrderId └── Amount

This repository represents: Where the change originates. The demo PR changes this contract so Blast Radius can trace the change to both consumer repositories.

# 4. Consumer 1 Demo Repository

## Repository 3 — blast-radius-demo-consumer-1

Purpose: demonstrate a downstream C# consumer affected by the producer/API change. It contains the consumer implementation, its local contract usage, unit/integration tests, and a clear relationship to Repository 2.

OrderConsumer ↓ OrderCreated

Consumer 1 should deliberately use the changed field so the breaking scenario produces an evidence-backed impact verdict and, when configured, a focused failing test.

# 5. Consumer 2 Demo Repository

## Repository 4 — blast-radius-demo-consumer-2

Purpose: demonstrate another downstream C# consumer. It contains its own implementation, contract usage and tests. It may consume the same contract without reading the changed field, allowing the final graph and report to show a different impact verdict.

Producer/API │ ├────────→ Consumer 1 │ └────────→ Consumer 2

Keeping the repositories separate simulates real cross-repository dependencies, demonstrates downstream impact, keeps Blast Radius reusable, and prevents the analyzer from becoming coupled to application code.

Separate repositories blast-radius is the reusable analyzer. The three C#/.NET demo repositories are application inputs checked out and analyzed by configuration; they do not contain Blast Radius implementation code.

| Repository | Role | Relationship |
| --- | --- | --- |
| blast-radius | Analyzer, orchestrator, graph, AI, report and Streamlit | Reads all registered repositories |
| blast-radius-demo-api | Producer/API and source contract | Publishes or exposes OrderCreated |
| blast-radius-demo-consumer-1 | Downstream consumer | Consumes OrderCreated and is intentionally affected |
| blast-radius-demo-consumer-2 | Downstream consumer | Consumes OrderCreated and demonstrates a second verdict |

# 6. Repository Workstream Mapping

Workstreamship identifies the first responder and reviewer for a repository; it does not mean only one person may modify it. All six team members should contribute through small, reviewed pull requests where appropriate.

| Repository | Primary workstream | Supporting workstreams | Purpose |
| --- | --- | --- | --- |
| blast-radius | Core Orchestration & Integration | All | Actual reusable analyzer |
| blast-radius-demo-api | Contract & Change Analysis | Test Intelligence | Producer/API |
| blast-radius-demo-consumer-1 | Dependency & Impact Analysis | Test Intelligence | Consumer |
| blast-radius-demo-consumer-2 | Dependency & Impact Analysis | Test Intelligence | Consumer |

# 7. Six Workstreams

| Team member | Primary responsibilities |
| --- | --- |
| Core Orchestration & Integration — Core Orchestration & Integration | Overall architecture; Python project skeleton; orchestrator; shared Pydantic contracts; configuration integration; GitHub Actions integration; cross-module integration; code review; E2E workflow; integration testing; final demo integration. Secondary: resolve cross-team blockers, maintain technical consistency and ensure modules follow agreed contracts. |
| Contract & Change Analysis — Contract & Change Analysis | Git diff analysis; changed file identification; changed symbols and contract identification; OpenAPI analysis; oasdiff integration where applicable; breaking/non-breaking rules; contract change output. |
| Dependency & Impact Analysis — Dependency & Impact Analysis | Service dependency configuration; NetworkX graph; JSON graph; consumer relationships; downstream traversal; impacted service identification; Mermaid visualization. |
| AI Analysis — AI Analysis | Provider-agnostic LLM abstraction; enterprise-approved LLM integration; prompt management; Pydantic schemas; JSON validation; Contract Analysis AI; Consumer Impact AI; Test Analysis AI; Failure Analysis AI; Report Generation AI; AI guardrails. |
| Test Intelligence — Test Intelligence | Test discovery; test mapping; relevant test selection; existing repository test commands; test execution; result and log collection; failure detection; failure-analysis input preparation; test validation. |
| UI & Documentation — UI & Documentation | Streamlit dashboard; report presentation; risk summary; dependency graph display; test results display; README; setup and configuration documentation; demo scenario; demo script; final presentation material. |

# 8. Required Prerequisites

## Developer prerequisites

Git

GitHub account and organization access

Python 3.12

pip and virtual environment tooling

VS Code or IntelliJ/PyCharm equivalent

GitHub CLI (gh), if approved

Docker only if genuinely required; it is not mandatory for the MVP

The required C#/.NET SDK for the demo repositories

Browser access to GitHub

Access to the enterprise-approved LLM

Access to the team repositories

## Python dependencies

networkx

pydantic

PyYAML

GitHub API/client library if required

Streamlit

OpenAPI/oasdiff integration where applicable

An appropriate Python testing framework

The LLM SDK corresponding to the enterprise-approved provider

Dependency boundary Python dependencies are used by Blast Radius. C#/.NET SDKs, application packages and test frameworks are used only by the three demo application repositories. Do not make the analyzer depend on a project reference into another repository.

# 9. GitHub Prerequisites & Approvals

Do not assume organization permissions are automatically available. Confirm the following before implementation begins, and record the answer in the team setup notes.

## Repository permissions

Create repositories, or request repository creation

Clone repositories

Create branches

Push branches

Create pull requests

Review pull requests

Merge pull requests

Configure repository settings if required

## GitHub Actions permissions

Run GitHub Actions

Create workflow files

Modify workflow permissions

Use reusable workflows/actions

Access required GitHub Actions secrets

Use the GitHub API from Actions

Post PR comments

## GitHub token permissions

Use least privilege. Likely needs are read repository contents, read pull request metadata, read changed files/diff information, write PR comments when the workflow posts reports, and read workflow/test information if needed. Do not request unrestricted repository administration unless a confirmed requirement emerges.

## Organization approval checklist

| Approval / access | Required? | Workstream to confirm | When needed |
| --- | --- | --- | --- |
| Repository creation | Confirm | GitHub/org admin | Day 1 |
| GitHub Actions enabled | Confirm | GitHub/org admin | Day 1 |
| Workflow permissions | Confirm | GitHub/org admin | Day 1 |
| PR comment permission | Confirm | GitHub/org admin | Week 1 |
| Secrets access | Confirm | Platform/admin | Week 1 |
| Enterprise LLM access | Confirm | AI/platform owner | Week 1 |
| External package installation | Confirm | Security/platform | Day 1 |
| C#/.NET SDK availability | Confirm | Team | Day 1 |

# 10. Secrets & Security

The minimum runtime configuration is an LLM API credential and a GitHub token or GitHub App credential. Exact names are agreed during Day 1 setup and kept out of source control.

LLM API credential GitHub token/app credential

Never hard-code secrets.

Never commit credentials, tokens or API keys.

Use GitHub Actions Secrets or an organization-approved secret mechanism.

Use environment variables or approved secret storage for local development.

Do not expose secrets through Streamlit.

Do not print secrets in logs or report artifacts.

Use least-privilege GitHub permissions.

Send only the minimum relevant diff and code excerpts to the enterprise-approved LLM.

# 11. GitHub Branching Strategy

main │ ├── feature/contract-analysis ├── feature/dependency-graph ├── feature/ai-analysis ├── feature/test-intelligence └── feature/streamlit

Do not develop directly on main.

Each feature goes through a pull request.

Keep pull requests small and reviewable.

Merge frequently to expose integration problems early.

Avoid long-lived branches.

Integration happens continuously. Cross-module integration is handled collaboratively through the Core Orchestration & Integration workstream and the shared module contracts.

Use the same lightweight approach for changes in the three demo repositories.

# 12. Configuration Design

| Path | Purpose |
| --- | --- |
| config/services.yaml | Registry of producer and consumer repositories, contract sources, owners, test projects and relationships. |
| config/rules.yaml | Deterministic change classifications and risk rules, including breaking, potentially breaking, additive and internal changes. |
| prompts/ | Versioned prompts for contract analysis, consumer impact, test analysis, failure analysis and report generation. |

services: - name: order-api repository: blast-radius-demo-api type: producer - name: order-consumer-1 repository: blast-radius-demo-consumer-1 type: consumer consumes: - order-api - name: order-consumer-2 repository: blast-radius-demo-consumer-2 type: consumer consumes: - order-api

Configuration must allow the analyzer to be reused for different repositories without changing core Python code. Repository-specific paths, test commands, owners and policy overrides belong in configuration; generic orchestration and analysis belong in the analyzer.

# 13. Shared Data Contracts

Define these minimal Pydantic models before detailed parallel development. They are the handshake between the six workstreams and prevent each module from inventing a private data shape.

| Model | Minimum fields | Input → processing → output |
| --- | --- | --- |
| PRInput | repository, pull_request, base_sha, head_sha | GitHub event → normalize context → stable PR context |
| ChangedArtifact | path, kind, base_text, head_text | Git diff → classify file → changed artifact |
| ContractChange | contract, member, before, after, classification, evidence | Artifact → contract comparison → typed change |
| DependencyNode | id, kind, repository, path | Source/config → graph node → NetworkX node |
| DependencyEdge | source, target, relationship, evidence | Consumer/config → relationship → NetworkX edge |
| ImpactedConsumer | repository, path, verdict, reason, evidence | Graph trace + code → verdict → consumer impact |
| TestCandidate | repository, command, selector, reason | Impact graph → map tests → runnable candidate |
| TestResult | repository, command, status, duration, logs | Candidate → test command → captured result |
| FailureAnalysis | related_to_change, component, cause, suggested_fix | Failure evidence → AI reasoning → explanation |
| RiskAssessment | level, score_inputs, recommendation | Changes + impacts + tests → rules → risk |
| BlastRadiusReport | risk, changes, consumers, tests, failures, reviewers | All outputs → render → PR/Streamlit report |

Parallel development rule Every module documents its Input → Processing → Output contract and uses the shared Pydantic models. Any contract change is made through a reviewed pull request with the affected workstreams involved.

# 14. Week 1 — Foundation

Theme: build the foundation and a vertical slice. The week ends with the complete pipeline executing, even if some intelligence is still basic.

## Day 1 — Alignment & Setup

Confirm MVP scope, four repositories, demo scenario and six owners.

Confirm GitHub permissions, LLM access, required SDKs and repository naming.

Agree on branching strategy and shared schemas.

Create the four repositories.

Initialize blast-radius and the three demo repositories.

Create the Python environment, project structure, configuration files and placeholder modules.

Create the GitHub Action skeleton and initial README.

End-of-day goal All four repositories exist and the team can clone, branch, commit, push and create pull requests.

## Days 2–3

| Workstream | Work |
| --- | --- |
| Core Orchestration & Integration | Orchestrator skeleton, shared models, configuration loading |
| Contract & Change Analysis | Git diff prototype and change detection |
| Dependency & Impact Analysis | NetworkX graph prototype and dependency JSON |
| AI Analysis | LLM interface and first Pydantic AI response |
| Test Intelligence | Test discovery and execution prototype |
| UI & Documentation | Streamlit skeleton and basic report UI |

## Days 4–5

PR/change ↓ Python orchestrator ↓ Change analysis ↓ Dependency analysis ↓ AI placeholder/analysis ↓ Test placeholder/execution ↓ Basic report

Week 1 deliverable End-to-end vertical slice. The complete pipeline must execute from a representative change to a basic report.

# 15. Week 2 — Core Implementation

Theme: replace prototypes with working MVP functionality. A real PR should produce a meaningful Blast Radius analysis by the end of the week.

| Workstream | Week 2 plan |
| --- | --- |
| Core Orchestration & Integration | Integration, GitHub Actions, configuration and orchestrator improvements. |
| Contract & Change Analysis | Complete change/contract analysis, breaking-change rules and OpenAPI/oasdiff. |
| Dependency & Impact Analysis | Complete NetworkX graph, consumer discovery, downstream traversal and Mermaid. |
| AI Analysis | Implement five AI modules, structured JSON, prompt versioning and guardrails. |
| Test Intelligence | Test selection, test execution, result parsing and failure identification. |
| UI & Documentation | Connect Streamlit to real outputs and display risk, graph, tests and report. |

Week 2 milestone A real PR produces a meaningful Blast Radius analysis, including changed contract, impacted consumers, selected tests, results and risk summary.

# 16. Week 3 — Integration & Stabilization

Theme: make the MVP reliable and demo-ready. Focus on E2E integration, bug fixing, prompt tuning, test validation, GitHub Action reliability, UI polish, documentation and demo preparation. Do not spend Week 3 introducing major new architecture.

| Day | Focus | Exit condition |
| --- | --- | --- |
| Day 11 | Full E2E integration: open a PR, run GitHub Actions, generate the report and display it in Streamlit. | One complete run works with captured artifacts and no hidden manual steps. |
| Day 12 | Breaking and non-breaking scenarios; verify deterministic rules and consumer verdicts. | The breaking scenario is high risk and the additive scenario is not falsely high risk. |
| Day 13 | Failure scenarios and AI explanation; validate evidence, proposed fix and guardrails. | A known failing test is related to the change and explained with cited evidence. |
| Day 14 | Final bug fixing, documentation and demo rehearsal. | README, setup steps and demo script are usable by another developer. |
| Day 15 | MVP freeze, final E2E run and presentation/demo. | Definition of Done is checked and the team presents a reproducible workflow. |

# 17. Demo Scenario

Use one controlled scenario so the team can validate every stage of the pipeline without ambiguity.

Repo 1: Order API ↓ OrderCreated contract ↓ Repo 2: Order Consumer ↓ Repo 3: Reporting Consumer

## Breaking scenario

The developer changes Amount to TotalAmount in the producer contract. Blast Radius should identify the changed contract, classify the change as potentially breaking or breaking, identify Consumer 1 and Consumer 2, select relevant tests, report intentional failures, provide an AI explanation, calculate risk and post the final PR report.

## Non-breaking scenario

The developer adds a new optional field that existing consumers do not read. Blast Radius should identify the additive change, show consumers as unaffected or safe, select only relevant coverage if any, and avoid treating every contract change as HIGH risk.

| Evidence to show | Expected result |
| --- | --- |
| Changed contract | Amount → TotalAmount, with file and line evidence |
| Consumer impact | Consumer 1 and Consumer 2 are listed with separate verdicts |
| Relevant tests | Only tests reachable from affected handlers are selected |
| Failure analysis | Intentional failing test is related to the change and explained |
| Risk summary | Risk reflects deterministic classification, consumer verdicts and test results |
| Final delivery | Upserted GitHub PR comment and matching Streamlit dashboard |

# 18. Integration Architecture

Integration architecture GitHub PR -> GitHub Actions -> Python Orchestrator -> Git/Contract Analysis + Dependency/Impact Analysis + AI Analysis -> Test Intelligence -> Test Execution -> Failure Analysis -> Risk Report -> GitHub PR Comment and Streamlit Dashboard.

| Stage | Implementation responsibility | Output |
| --- | --- | --- |
| Trigger | GitHub PR workflow and checkout | PRInput |
| Facts | Git diff, OpenAPI/oasdiff and deterministic rules | ContractChange |
| Impact | NetworkX graph traversal and consumer mapping | ImpactedConsumer |
| Reasoning | Provider-agnostic LLM with Pydantic/JSON validation | Structured AI results |
| Tests | Existing repository test command and result parsing | TestResult |
| Delivery | Risk report, PR comment and Streamlit view | BlastRadiusReport |

Separate repositories blast-radius is the reusable analyzer. The three C#/.NET demo repositories are application inputs checked out and analyzed by configuration; they do not contain Blast Radius implementation code.

| Repository | Role | Relationship |
| --- | --- | --- |
| blast-radius | Analyzer, orchestrator, graph, AI, report and Streamlit | Reads all registered repositories |
| blast-radius-demo-api | Producer/API and source contract | Publishes or exposes OrderCreated |
| blast-radius-demo-consumer-1 | Downstream consumer | Consumes OrderCreated and is intentionally affected |
| blast-radius-demo-consumer-2 | Downstream consumer | Consumes OrderCreated and demonstrates a second verdict |

The three demo repositories remain application inputs to the analyzer. The blast-radius repository owns orchestration and report behavior. GitHub Actions provides the MVP trigger and runtime; no dedicated backend server is required.

# 19. Dependency Matrix

| Component | Depends on | Workstream | Required by |
| --- | --- | --- | --- |
| Orchestrator | Shared schemas/config | Core Orchestration & Integration | Week 1 |
| Change Analyzer | Git diff/OpenAPI | Contract & Change Analysis | Week 1–2 |
| Dependency Graph | services.yaml | Dependency & Impact Analysis | Week 1–2 |
| AI Modules | LLM access + schemas | AI Analysis | Week 1–2 |
| Test Intelligence | Demo repo tests | Test Intelligence | Week 1–2 |
| Streamlit | Analyzer outputs | UI & Documentation | Week 1–2 |
| GitHub Action | Orchestrator | Core Orchestration & Integration | Week 2 |
| Final Report | All modules | Persons 1, 4, 6 | Week 2–3 |

# 20. Cross-Team Dependency Rules

| Dependency | Rule |
| --- | --- |
| Contract & Change Analysis → Dependency & Impact Analysis | Changed contract information feeds dependency and impact analysis. |
| Dependency & Impact Analysis → AI Analysis | Impacted consumer information feeds AI consumer-impact reasoning. |
| Dependency & Impact Analysis → Test Intelligence | Impacted consumers help identify relevant tests. |
| Test Intelligence → AI Analysis | Test results and logs feed failure analysis. |
| Contract & Change Analysis + Dependency & Impact Analysis + AI Analysis + Test Intelligence → UI & Documentation | All structured outputs feed Streamlit and report generation. |
| Everyone → Core Orchestration & Integration | All workstreams contribute outputs that are integrated through the shared orchestration and module contracts. |

Integration cadence Merge small, contract-compatible pull requests frequently. When an output contract must change, update the Pydantic model, its consumer and a representative test in the same coordinated change.

# 21. Definition of Done

The MVP is complete only when every item below is true:

Four repositories are functional.

A GitHub PR triggers the workflow.

The Python orchestrator executes.

Git diff is analyzed.

Contract changes are detected.

OpenAPI/oasdiff works where applicable.

A NetworkX graph is generated.

Downstream consumers are identified.

AI analysis returns validated structured output.

Relevant tests are selected.

Existing repository test commands execute.

Test results are captured.

Failures are analyzed.

A risk summary is generated.

A PR comment is produced.

Streamlit displays the result.

Configuration supports the three demo repositories.

README and setup documentation are complete.

At least one breaking and one non-breaking scenario are demonstrated.

## Risks and mitigations

| Risk | Mitigation |
| --- | --- |
| Missing GitHub or LLM access delays the schedule | Confirm access on Day 1; use deterministic fixtures and a local/mock provider boundary for development until approval arrives. |
| Consumer code is not linked by a build reference | Use services.yaml, contract attributes/conventions, lightweight parsing and graph evidence. |
| AI produces unsupported claims | Require Pydantic/JSON output, cited file/line evidence and deterministic guardrails; AI may not lower a deterministic breaking result. |
| Focused tests are incomplete | Keep a configurable full-suite fallback and make coverage gaps visible in the report. |
| Cross-team interfaces drift | Use shared models, small PRs, frequent integration and Core Orchestration & Integration coordination. |

# 22. What We Should NOT Build

Protect the three-week schedule from scope creep. Do not introduce:

Azure DevOps

Azure-specific CI/CD

Kubernetes

Microservices

Graph database

Vector database

LangChain/LangGraph

Complex autonomous agents

Dedicated backend server

Multi-language analysis

Enterprise-scale deployment

Multi-CI-platform support

Production-grade authentication platform

MVP boundary GitHub + GitHub Actions + Python 3.12 + Streamlit + NetworkX + OpenAPI/oasdiff + Pydantic/JSON + provider-agnostic enterprise LLM + existing repository test frameworks.

# 23. Final Checklist Before Coding Starts

## Access

[ ] GitHub organization access

[ ] Repository creation/access confirmed

[ ] GitHub Actions enabled

[ ] Workflow permissions confirmed

[ ] PR comment permission confirmed

[ ] Required secrets mechanism confirmed

[ ] Enterprise LLM access confirmed

## Local setup

[ ] Python 3.12 installed

[ ] Git installed

[ ] GitHub CLI available if approved

[ ] C#/.NET SDK installed

[ ] IDE configured

[ ] Python virtual environment created

## Repositories

[ ] blast-radius

[ ] blast-radius-demo-api

[ ] blast-radius-demo-consumer-1

[ ] blast-radius-demo-consumer-2

## Architecture

[ ] Shared Pydantic models agreed

[ ] services.yaml agreed

[ ] rules.yaml agreed

[ ] AI input/output contracts agreed

[ ] Test execution contract agreed

[ ] Report structure agreed

## Demo

[ ] Producer scenario selected

[ ] Consumer relationships defined

[ ] Breaking change defined

[ ] Non-breaking change defined

[ ] Expected test failure defined

[ ] Expected final report defined